## Project Timeline
Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Milestone | Assigned To | Position | Baseline | Project Timeline Tip
2021-10-01 | Project Start |  | 10 | 0 | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2021-10-20 | Model ready |  | 20 | 0
2021-10-26 | MVC |  | -10 | 0
2021-10-27 | Simulation |  | 20 | 0
2021-11-01 | Measure in LAB |  | 10 | 0
2021-11-05 | Controller design - PI |  | 20 | 0
2021-11-12 | Controller design - LQR |  | 10 | 0
2021-11-16 | STOK |  | -10 | 0
2021-11-18 | Controller design - MPC |  | 20 | 0
2021-11-25 | Controller Test |  | 10 | 0
2021-11-26 | Artikel+Abstract |  | 20 | 0
2021-11-29 | DRTS |  | -10 | 0
2021-12-08 | Review(s) |  | 20 | 0
2021-12-15 | Project done |  | 20 | 0
2021-12-17 | Project delivery |  | 10 | 0
2021-12-21 | SEMCON |  | 20 | 0
2022-01-01 | Project End |  | 10 | 0
0